## WBS_Est_Day01
|  |  |  | 1 Point estimation technique | 3 Point estimation technique |  |  | (Beta)3+4*5+7=30/6 | Standard Deviation
WBS |  |  | Activity | NO. Days | Optimistic value | Most Likely value | Pessimistic value | Average | Pv-Os=(..)/6 | Square root 0.66*0.66
Level 1 | Level 2 Elements | Level 3 Elements | 1.1.1 Estimate cost | 4 | 3 | 5 | 7 | 5 | 0.66 | 0.435
Slante Care |  |  | 1.1.2 Establish Budget | 6 | 5 | 7 | 9 | 7 | 0.66 | 0.435
| 1.0 Project Management |  | 1.2.1 Develope preliminary design | 14 | 10 | 13 | 20 | 13.66 | 1.66 | 2.755
1.1 Budget
|  | 1.2 Design | 1.2.2 Review and change | 5 | 3 | 6 | 9 | 6 | 1 | 1
|  | 1.3 Permits | 1.2.3 Finalize design | 2 | 2 | 4 | 5 | 3.83 | 0.5 | 0.25
1.4 Sub contractor Management.
| 2.0 Project Development | 2.1 Requirement | 1.3.1 Apply for approval | 7 | 5 | 9 | 15 | 9.33 | 1.66 | 2.755
|  | 2.2 Feasibility study | 1.3.2 Procure approval | 2 | 2 | 5 | 4 | 4.33 | 0.33 | 0.108
|  | 2.3 Design | 1.3.3 Co-ordinate with scrum team. | 2 | 1 | 3 | 5 | 3 | 0.66 | 0.435
|  | 2.4 Coding | 1.3.4 Hire core team and share team. | 15 | 10 | 22 | 25 | 20.5 | 2.5 | 6.25
|  | 2.5 Testing | 1.3.5 Perform final walkthrough. | 4 | 2 | 6 | 8 | 5.66 | 1 | 1
|  | 2.6 Release |  | Total=56 |  |  |  | Estimate=78.31 |  | 15.423
Square root of 15.423 is =3.927
[7 empty] | Estimate Range | 66.529 | 90.091
Reamrks: Using 3 pointer estimation technique, compitence is 99% between the range of 66 to 91. Poject will be done